Eagle Project Plan Check-Sheet

Scout’s Name: ______________________ Troop: _________ Date: _____________

Project Documents (All completed In Ink)

O Project booklet used (Original booklet is preferred.)

O Extra pages attached

O Eagle Scout Leadership Project Application Cover Sheet completed/attached (Blue page)

Project Description

O Describe project

O What group will benefit?

O How will group benefit?

O Date discussed with unit leader

O Name and title of group representative

Plan Your Project (Describe details of plan and minimum requirements. “Wait to see who shows up,” isn’t a plan.)

O Describe present condition

O Describe method to be used (A thorough task analysis required, identifying & listing all tasks and subtasks.)

O List work teams required for each task (Min number of adults, older, and younger scouts needed for ea.)

O Estimate the total number of labor hours required for each task/part of project (Hawkeye Area

Council RECOMMENDS 100 total project hours as a target. Show how you get there.)

O Estimate labor cost if the work would have been contracted to a business (Use minimum wage of $5.15 if unable to get an estimate from a business.)

O Describe/list materials to be used (Don’t forget preparation and clean-up needs.)

O Build a table matrix that lists:

O Tools needed (Examples) Quant Cost P/D/B

Tools (hammers) 2 $0.00 B

Supplies (nails) 100 $2.00 P

Materials (2x4x8) 10 $15.00 D

O Supplies needed

O Materials needed

O Estimated Quantities of each

O Estimated Cost of each

O List whether item is Purchased, Donated, Borrowed

O List projected total cost savings to group benefiting from this effort (includes labor and materials).

O List start/finish dates of labor

O Estimated start/stop times for each day

O Daily time schedule for work, meals, and breaks

O Describe Safety Hazards (High/Low temps, debris, chemicals, blisters, insects, power tools {Restricted})

O List Safety Precautions in place (goggles, gloves, glasses, shoes/boots, water/drinks, power tools,

first aid kits, phone access, Who is Designated Medic?)

O Describe procedures for contacting emergency and evacuation assistance if needed.

O Include drawings/sketches/photos to help describe the project effort.

Project Plan Approval:

O Group and unit representative signatures (Originals in project booklet)

O District or Council Advancement Committee member signature (Originals in project booklet)

Immediately After the Project:

O Turn a copy of the volunteer roster to the Advancement Chair so the participating Scouts receive the Service hours credit

O Begin drafting the details of the Project so the details are not forgotten (what went well as well as improvements that could have been made)

Hawkeye Area Council Version 3: 11-16-04